## Sheet1
Profile #1 - Ideal Design, fully featured (v1), includes cloud hardening, release management for feature enhancements ready, scalable etc.
Resource | Description | Hourly rate | hours | total cost
User Interface Designer | Designs screens, visual styles, user interface | 100 | 480
Cloud Engineer | Landing Zone Design, Cloud Platform setup, Pipeline support, CI\CD | 100 | 480
Front End Dev | Turn interface designs into services & code | 100 | 480
Back End Data Developer | Develops services responsible for passing data from Front End to cache \ storage | 100 | 480
Release \ Product Manager | Release management, Pipeline management | 100 | 480
Security & Cloud Specialist | Validate Cloud best practice, SOC & complaince, Webstandards Oauth \ OIDC | 100 | 480
Service Designer \ Business Analyst | Service Design, User Process Flow | 100 | 480
API \ Integration Developer | API wrappers, end point configuration, security | 100 | 480
|  | 800 | 3840 | 3072000
Profile #2 - Functionally working design. Potential tech debt. Basic release management & security posture. Conservative quotas on APIs, somewhat scalable.
Resource | Description | Hourly rate | hours | total cost
User Interface Designer & Service Designer \ Business Analyst | Designs screens, visual styles, user interface Service Design, User Process Flow | 100 | 480
Full stack Dev(x3) | Landing Zone Design, Cloud Platform setup, Pipeline support, CI\CD API wrappers, end point configuration, security Turn interface designs into services & code | 300 | 480
Release \ Product Manager | Release management, Pipeline management | 100 | 480
Security & Cloud Specialist | Validate Cloud best practice, SOC & complaince, Webstandards Oauth \ OIDC Landing Zone Design, Cloud Platform setup, Pipeline support, CI\CD | 100 | 480
|  | 600 | 1920 | 1152000
Profile #3 - MVP design, Screen facades with basic functionality, i.e. limited IDP support, basic backend to support feature demonstration or showcase. Figma flows for some enhancement feature demonstration.
Resource | Description | Hourly rate | hours | total cost
User Interface Designer & Service Designer \ Business Analyst | Designs screens, visual styles, user interface Service Design, User Process Flow | 100 | 160
Full stack Dev(x2) | Landing Zone Design, Cloud Platform setup, Pipeline support, CI\CD API wrappers, end point configuration, security Turn interface designs into services & code | 200 | 160
Security & Cloud Specialist | Validate Cloud best practice, SOC & complaince, Webstandards Oauth \ OIDC Landing Zone Design, Cloud Platform setup, Pipeline support, CI\CD | 100 | 160
|  | 400 | 480 | 192000
Profile #4 - Facade design, Screen facades with all functionality,no backend. Figma flows for all feature demonstration.
Resource | Description | Hourly rate | hours | total cost
User Interface Designer & Service Designer \ Business Analyst (x3) | Designs screens, visual styles, user interface Service Design, User Process Flow | 300 | 160
|  | 300 | 160 | 48000